## Sheet1
Status Report (15/6/2015 - 27/6/2015)
Tasks Worked
1 | UI Designing (Login and Registration screen)
Period:
| 15-June-2015 to 20-June 2015 |  | (Hours of Development: 30 Hours)
Details:
| 1 | Designing of the Login Page
| 2 | Designing of the Registration Page (Buyer)
| 3 | Designing of the Registration Page (Business Owner)
| 4 | Integrating the two pages
| 5 | Performing final coding of the integration
Issues:
| 1 | Forgot Password Implementation not done (as on date till 20-June-2015)
Risk:
| 1 | Further changes in UI because of requirement changes
2 | Setting up the server
Period:
| 21-June-2015 to 21-June-2015 |  | (Hours of Development: 4 Hours)
Details:
| 1 | Finding out the free webhosting service with maximum features
| 2 | Setting up a account and starting the service
| 3 | Setting up a domain and other formalities
| 4 | Designing of the database and tables
Issues:
None
Risk:
| 1 | Free webhosting is temporarily down hindering the development
3 | Server Side coding for login and Registration
Period:
| 21-June-2015 to till date |  | (Hours of Development: 12 Hours)
Details:
| 1 | PHP code for the server required for the connection of the android app and remote database
| 2 | Testing of the PHP code
Issues:
| 1 | Handling of multiple tables by the remote database
Risk:
None
4 | Client Side coding
Period:
| 21-June-2015 to till date |  | (Hours of Development: 15 Hours)
Details:
| 1 | Coding for the android app to send data to the remote database
| 2 | JSON encoding
| 3 | Code for receiving data from the remote database
| 4 | Other coding parts necessary
Issues:
None
Risk:
None
5 | Implementing Forgot Password
| Period: 18-June-2015 to 19-June-2015 |  |  | (Hours of Development: 4 Hours)
Details:
| 1 | Discussion over the method of implementation of forgot password module
| 2 | Implementing the security question and security answer as the method
Issues:
None
Risk:
None
Total Hours Worked
Period: |  | 15/06/2015 to 27/06/2015
Hours Worked: |  | 65 hours
Tasks Planned
No new tasks planned
Completing the login and registration by 7-July-2015